## Example
EXAMPLE ONLY
5-Year Tactic Template
Provide goals and direction for how to foster environmentally and socially responsible purchasing
Responsible Unit(s) | Purchasing Office
Performance Indicator/Metric: | x% increase of sustainable purchases on campus
Progress Tracker (position responsible for tracking regular progress on strategies/tactics) | Asst. Purchasing Director
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Develop a tracking system for sustainable purchases on campus
Establish the criteria for tracking purchases (e.g. Energy Star, Green, FSC, certified, GreenSeal, etc.) | Asst. Purchasing Director | Criteria established by Dec. 2010 | Inclusion in NC State's proposed Sustainability Policy
Create standard language for bid proposals over $5,000 and convenience contracts | Purchasing Director | Language created and approved by Feb. 2011 | Clarification on the effect Executive Order 50 will have on local purchasing options
Include a sustainability checkbox or equivalent in the MarketPlace system | Asst. Purchasing Director | Language created and approved by Feb. 2011 | None
Require MarketPlace vendors to submit data annual data on sustainable purchases from NC State | Asst. Purchasing Director | Implement first round of reporting in May 2011. | NC State policy directing this reporting (inclusion in NC State's proposed Sustainability Policy)
Create a data reporting template in line with DENR requirements for use for MarketPlace vendor annual reporting | Purchasing Administrative Assistant | Created and approved by Feb. 2011 | None
Help campus increase the amount of sustainable materials purchased
Tactic 1
Tactic 2
Tactic x…
Work with MarketPlace vendors to highlight sustainable items on their electronic ordering sites
Tactic 1
Tactic 2
Tactic x…
Create incentives for purchase of more sustainable products and services
Tactic 1
Tactic 2
Tactic x…

## Blank template
5-Year Tactic Template
Strategy
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Sub Strategy 1
Tactic 1
Tactic 2
Tactic x….
Sub Strategy 2
Tactic 1
Tactic 2
Tactic x…
Sub Strategy 3
Tactic 1
Tactic 2
Tactic x…
Sub Strategy x
Tactic 1
Tactic 2
Tactic x…

## Buildings
Buildings Working Group Tactic Brainstorm, May 14, 2010
Attendees:
Buildings Working Group Tactic Development, May 14, 2010
Attendance: Carole Acquesta, Rachel Miller, Barry Joyce, Bill Davis, Tracy Dixon, Lindsay Batchelor, Ed Rogers, Kevin Cummings, Lisa Maune, Dona Stankus
Notes: Working group brainstormed possible tactics. Decided to start with two of the easier tactics before moving to the others. Tracy and Lindsay attempt to condense some of the tactics prior to the next meeting. Next meeting Tuesday, May 25 at 3-430, June 15, June 29. Meeting requests to follow.
Apply sustainable practices to all buildings and renovations, including private buildings
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Undertake holistic building renovations that include conservation of all natural resources
retrocommisisoning -
Tactic 2
Tactic x….
Uphold NC State’s commitment to build LEED silver minimum buildings for all projects over 20,000 gross square feet (strive for higher certification levels)
Require design and construction contracts to meet LEED silver
Administrative requirement (VC Leffler)
Prepare for in advanced planning
Monitor compliance throughout design and construction process
Designers selection - experienced in sustainability
Project manager commitment
Tie sustainability to quality
what about buildings over 20,000 sf and/or $2m? - Set expectations for all projects
Professional oversight for life of building-comprehensive commissioning
Encourage granting agencies to include sustainability in funding
Standards for all buildings (includes prototype/baseline, campus credits, supporting regional approaches, encouraging innovative/emerging technology)
Investigate alternative financing means
Get legislation to support these efforts
Incentives for groups to achieve higher levels of certification
Tie standards to design and construction guidelines (update)
Work with NCSU foundation to look at donor model to help fund renewables and other technologies
Monitor what are funding mechanism opportunities
Include leveraging tax credits in design contract
Passive design strategies (orientation, daylight) as part of master planning process. Land use that favors passive solar orientation.
Training, education, and funding to get buy in of new technology use, operation, and maintenance.
Operation and maintenance budgets need to include room to maintain these newer technologies
Work on accounting model of who maintains what (where shared, savings not always going into best bucket). Example of retention ponds.
Look at additional standards beyond LEED in long term for climate neutrality (what's next, where is the industry going, example Living Building Challenge - net zero energy, water, etc)
Have university representative in International Code Council meetings that are determining sustainability and energy codes
Encourage private buildings on NC State land to uphold NC State’s sustainability principles
Tactic 1
Tactic 2
Tactic x…
Design and construct flexible spaces that can be easily repurposed
Tactic 1
Tactic 2
Tactic x…
Adopt a sustainability vision statement or include it as part of the scope statement for all projects
Determine a consistent processes for formal and informal projects
Obtain approval of building committee and other stakeholders
Create a template for project types
LEED pilot program that gradually gains credits for campus
Strategies that work across groups and should be given consideration in your working group
See land use tab - Enhance the utilization and management of campus and building space
See integration tab - Adopt an aggressive sustainability policy
See integration tab - Instill the values of total cost of ownership and total life cycle costing in to purchasing and project decision making
See integration tab - Investigate funding opportunities that further sustainability
See integration tab - Update university guiding documents such as the master plan and design and construction guidelines to include sustainability principles
See integration tab - Continue to work with the Legislature, General Administration and other entities to further mechanisms that enable the university to meet laws
See outreach tab - Begin establishing a campus culture that embraces personal responsibility and emphasizes action in creating a sustainable campus and community
See outreach tab - Make campus-wide sustainability efforts and progress more visible
See outreach tab - Develop a procedure for integrating sustainability teaching, research and extension expertise into physical campus projects

## Energy and Water
5-Year Tactic Template
Achieve a 20% reduction in building energy consumption by 2015 (target reduction to 137,510 BTUs/GSF), with a stretch goal of achieving a 30% reduction (target reduction to 120,322 BTUs/GSF), compared to the 2002-2003 baseline (171,888 BTUs/GSF)
Responsible Unit(s) | NC State Facilities Operations
Performance Indicator/Metric: | BTUs/GSF
Progress Tracker (position responsible for tracking regular progress on strategies/tactics) | Utilities Engineering, Energy Management
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Install Combined Heat & Power Plant at Cates and new boilers at Yarbrough central plants. | Utilities Engineering | 2012 | Performance Contract
Execute Building Peformance Contracting for 13 buildings | Facilities Operations | 2011 | Performance Contract
Solicity new Performace Contract for 6 to 8 more buildings | Facilities Operations | 2012 | Performance Contract
Install a comprehensive campus energy dashboard | Facilities Operations | TBD | TBD
Modernize existing and install new data centers | OIT | TBD | TBD
Develop a comprehensive campus energy charge. | CEST | 2010 | TBD
Achieve a 45% reduction in building water consumption through 2015 (target reduction to 0.0363 CCF/GSF), with a stretch goal of achieving a 50% reduction (target reduction to 0.033 CCF/GSF), compared to the 2001-2002 baseline (0.066 CCF/GSF)
Responsible Unit(s) | NC State Facilities Operations
Performance Indicator/Metric: | CCF/GSF
Progress Tracker (position responsible for tracking regular progress on strategies/tactics) | Utilities Engineering, Energy Management
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Develop a comprehensive campus water use dashboard | Utilities Engineering | TBD | TBD
Execute Building Peformance Contracting for 13 buildings | Facilities Operations | 2011 | Performance Contract
Solicity new Performace Contract for 6 to 8 more buildings | Facilities Operations | 2012 | Performance Contract
Install COR resue water service on Centennial Campus | Facilities Operations | 2012 | TBD
Install rainwater and condensate water collection systems at central plants | Facilities Operations | TBD | TBD
Execute campus stormwater master plan | Facilities Operations | 2011 | TBD
Create buy in with Facilities staff and building end-users to properly operate building systems in an energy efficient manner
Responsible Unit(s) | NC State Facilities Operations
Performance Indicator/Metric: | BTUs/GSF and CCF/GSF
Progress Tracker (position responsible for tracking regular progress on strategies/tactics) | Utilities Engineering, Energy Management
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Develop a comprehensive campus energy and water use dashboard | Utilities Engineering | TBD | TBD
tactic 2…
tactic 3…
Evaluate utility billing options that create incentives for saving energy
Responsible Unit(s) | NC State Facilities Operations
Performance Indicator/Metric: | BTUs/GSF and CCF/GSF
Progress Tracker (position responsible for tracking regular progress on strategies/tactics) | Utilities Engineering, Energy Management
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Develop a comprehensive campus energy and water use dashboard | Utilities Engineering | TBD | TBD
Implement Wolf Enterprise system | Utilities Engineering | TBD | TBD
tactic 3…
Use return on investment calculations to help prioritize and guide energy conservation projects (“energy smart” repairs)
Responsible Unit(s) | NC State Facilities Operations
Performance Indicator/Metric: | BTUs/GSF and CCF/GSF
Progress Tracker (position responsible for tracking regular progress on strategies/tactics) | Utilities Engineering, Energy Management
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Develop an Energy Policy | CEST | TBD | TBD
Standardize LCC models and templates | Business Services | TBD | TBD
tactic 3…
Further develop funding mechanisms, including Energy Performance Contracting as a means to achieve energy savings
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Implement green information technology standards and practices
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Embrace communications technology such as teleconferencing and video conferencing to reduce the need for travel
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Improve energy data management capability to make data-driven energy decisions
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Ensure a cost effective and stable energy supply by developing business scenarios and strategies for differing fuel sources
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Strategies that work across groups and should be given consideration in your working group
See land use tab - Enhance the utilization and management of campus and building space
See integration tab - Adopt an aggressive sustainability policy
See integration tab - Instill the values of total cost of ownership and total life cycle costing in to purchasing and project decision making
See integration tab - Investigate funding opportunities that further sustainability
See integration tab - Update university guiding documents such as the master plan and design and construction guidelines to include sustainability principles
See integration tab - Continue to work with the Legislature, General Administration and other entities to further mechanisms that enable the university to meet laws
See outreach tab - Begin establishing a campus culture that embraces personal responsibility and emphasizes action in creating a sustainable campus and community
See outreach tab - Make campus-wide sustainability efforts and progress more visible
See outreach tab - Develop a procedure for integrating sustainability teaching, research and extension expertise into physical campus projects

## Land Use
Land Use Tactic Development 4-5-10
Improve and enhance campus natural areas and habitats (discussion about definition needed for natural areas and habitats)
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Implement a restoration and conservation plan that identifies specific environmentally-sensitive land areas on campus, repairs negatively impacted natural areas, and establishes measures to preserve and protect them
Pilot management of invasives on North Creek Cooridor (Gene , Karen Hall, Tom Wenworth, other)
Tactic 2
Tactic x….
Enhance corridors for native habitats and wildlife
Tactic 1
Tactic 2
Tactic x…
Create and implement a tree conservation plan for each campus presincts
Lisa/Tom/Mike fill in dates/resources. One tactic per presinct
Tactic 2
Tactic x…
Develop a land management plan for Lake Raleigh Woods
Identify oversight committee (include Gary Blank) | Skolnicki's position
Draft the plan (students may draft plan through several semester) | Skolnicki's position
Engage to use as teaching area/students (Gary Blank)
Develop an urban forestry plan
Possible student project | Grounds Mngmt? Ratzliff might be mapping trees
Establish criteria for what urban forestry is. Many different views on what is urban forestry (carbon sequestration, teaching, heat island, etc). Possible forum to understand what want then establish pilot areas. (Susan Moore, Melissa McHale - find person passionate about this)
Update/reassess inventory based on criteria
Create management plan
Develop low impact site principles for new building and infrastructure projects that consider building site selection, utility corridor selections, building footprint, existing topography, etc.
Tactic 1
Tactic 2
Tactic x…
Create and administer a storm water master plan for campus in conjunction with the NC State Storm Water Programs
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Enhance utilization and management of campus and building space
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Develop a tool/metrics to use in managing space and space utilization to reduce future space needs
Tactic 1
Tactic 2
Tactic x….
Maximize campus existing building spaces to reduce the need for new buildings
Tactic 1
Tactic 2
Tactic x…
Embrace adaptive reuse of existing structures
Tactic 1
Tactic 2
Tactic x…
Create buildings with the smallest physical building footprint
Tactic 1
Tactic 2
Tactic x…
Optimize extended hours and weekly building usage and operation to reduce the need for new building space
Tactic 1
Tactic 2
Tactic x…
Improve capacity to adjust classroom size to enrollments
Tactic 1
Tactic 2
Tactic x…
Create walkable, mix-use neighborhoods to reduce the distance between necessary services
Tactic 1
Tactic 2
Tactic x…
Increase the acreage of campus open space
Tactic 1
Tactic 2
Tactic x…
Increase the percentage of undergraduate students living on campus from 33% to 40% so that fewer students are driving to and from campus daily (Transportation also has this strategy)
Tactic 1
Tactic 2
Tactic x…
Increase campus density?
Tactic 1
Tactic 2
Tactic x…
Partner with on-campus research units such as the Center for Integrated Pest Management to evaluate and enhance the NC State’s Integrated Pest Management Program to reduce reliance on chemical pest control
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Create new landscape design guidelines to ensure low maintenance landscapes are implemented
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Strategies that work across groups and should be given consideration in your working group
See integration tab - Adopt an aggressive sustainability policy
See integration tab - Instill the values of total cost of ownership and total life cycle costing in to purchasing and project decision making
See integration tab - Investigate funding opportunities that further sustainability
See integration tab - Update university guiding documents such as the master plan and design and construction guidelines to include sustainability principles
See integration tab - Continue to work with the Legislature, General Administration and other entities to further mechanisms that enable the university to meet laws
See outreach tab - Begin establishing a campus culture that embraces personal responsibility and emphasizes action in creating a sustainable campus and community
See outreach tab - Make campus-wide sustainability efforts and progress more visible
See outreach tab - Develop a procedure for integrating sustainability teaching, research and extension expertise into physical campus projects

## Transportation
5-Year Tactic Template
Develop functional elements of a longer -range (10-15 year) campus mobility vision detailing implementation actions to expand student/staff reliance on alternative transportation; reduce the need for new campus parking; enhance Main and Centennial campus precinct travel connectivity and ease; and alleviate traffic congestion on campus roadways and city streets, coming other topics
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Reduce the consumption of and demand for petroleum in university fleet
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Increase alternative fuel vehicles in university motor pool and departmental fleets
Tactic 1
Tactic 2
Tactic x….
Reduce vehicle fuel usage
Tactic 1
Tactic 2
Tactic x…
Continuously refine and market Wolfline services to accommodate increased rider demand and changing travel needs within and between campus precincts, especially Centennial to Main connections
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Decrease traffic congestion on main campus thoroughfares
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Institute additional daytime vehicle access restrictions on selected roadway segments
Tactic 1
Tactic 2
Tactic x….
Enhance Wolfline transit system speeds and schedule reliability
Tactic 1
Tactic 2
Tactic x…
Promote a safer walking and bicycling atmosphere
Tactic 1
Tactic 2
Tactic x…
Develop a plan addressing infrastructure and programs that promote additional bicycling and pedestrian trips between and among campuses
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Promote and increase use of Triangle Transit and Capital Area Transit services to campus, integrating operating schedules and coordinating transfers to and from Wolfline bus routes wherever possible
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Develop policies that reduce/limit parking supply requirements associated with campus precincts undergoing significant new development
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Reduce single occupancy vehicle trips to, from, and around campus
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Leverage parking permit pricing and policies to encourage a "park it and leave it" perimeter parking philosophy
Tactic 1
Tactic 2
Tactic x….
Increase both student and employee carpooling
Tactic 1
Tactic 2
Tactic x….
Shift unnecessary daytime single occupancy vehicle trips to Wolfline bus, bicycling, and pedestrian alternatives
Tactic 1
Tactic 2
Tactic x….
Intensify marketing for and reliance on free and low-cost campus perimeter parking facilities geared towards commuters
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Ensure above average frequency and dependability of transit connections from perimeter lots to core campus destinations
Tactic 1
Tactic 2
Tactic x….
Evaluate permit pricing and parking space/access incentives for expanding the number of Low Emitting Vehicles (LEV) being brought to campus
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Strategies that work across groups and should be given consideration in your working group
See land use tab - Enhance the utilization and management of campus and building space
See energy tab - Embrace communications technology such as teleconferencing and video conferencing to reduce the need for travel
See integration tab - Adopt an aggressive sustainability policy
See integration tab - Instill the values of total cost of ownership and total life cycle costing in to purchasing and project decision making
See integration tab - Investigate funding opportunities that further sustainability
See integration tab - Continue to work with the Legislature, General Administration and other entities to further mechanisms that enable the university to meet laws
See outreach tab - Begin establishing a campus culture that embraces personal responsibility and emphasizes action in creating a sustainable campus and community
See outreach tab - Make campus-wide sustainability efforts and progress more visible
See outreach tab - Develop a procedure for integrating sustainability teaching, research and extension expertise into physical campus projects

## Materials and Purchasing
5-Year Tactic Template
Provide goals and direction for how to foster environmentally friendly and socially responsible purchasing
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Help campus increase the amount of sustainable materials purchased
Tactic 1
Tactic 2
Tactic x….
Develop a tracking system for sustainable purchases on campus
Tactic 1
Tactic 2
Tactic x…
Work with MarketPlace vendors to highlight sustainable items on their electronic ordering sites
Tactic 1
Tactic 2
Tactic x…
Create incentives for purchase of more sustainable products and services
Tactic 1
Tactic 2
Tactic x…
Implement sustainable purchasing standards
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Help individual departments further develop the university’s sustainability policy to focus on specific needs
Tactic 1
Tactic 2
Tactic x….
Develop bid specifications that require vendors to provide sustainable options for their products
Tactic 1
Tactic 2
Tactic x…
Strategies that work across groups and should be given consideration in your working group
See waste reduction tab - Implement source reduction and environmentally friendly preferable purchasing initiatives to decrease waste before it happens
See integration tab - Adopt an aggressive sustainability policy
See integration tab - Instill the values of total cost of ownership and total life cycle costing in to purchasing and project decision making
See integration tab - Investigate funding opportunities that further sustainability
See integration tab - Continue to work with the Legislature, General Administration and other entities to further mechanisms that enable the university to meet laws
See outreach tab - Begin establishing a campus culture that embraces personal responsibility and emphasizes action in creating a sustainable campus and community
See outreach tab - Make campus-wide sustainability efforts and progress more visible
See outreach tab - Develop a procedure for integrating sustainability teaching, research and extension expertise into physical campus projects

## Waste Reduction
5-Year Tactic Template
Utilize modern collection concepts and practices to streamline services, improve programs and increase operational efficiencies and customer service
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Implement source reduction and environmentally friendly preferable purchasing initiatives to decrease waste before it happens
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Develop a more extensive outdoor walkway recycling program to capture additional recyclable materials and remove them from the waste stream
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Develop a comprehensive closed loop program to capture organic waste (food waste, animal bedding, yard waste, etc) for composting and utilize the composted product on campus
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Strategies that work across groups and should be given consideration in your working group
See integration tab - Adopt an aggressive sustainability policy
See integration tab - Instill the values of total cost of ownership and total life cycle costing in to purchasing and project decision making
See integration tab - Investigate funding opportunities that further sustainability
See integration tab - Continue to work with the Legislature, General Administration and other entities to further mechanisms that enable the university to meet laws
See outreach tab - Begin establishing a campus culture that embraces personal responsibility and emphasizes action in creating a sustainable campus and community
See outreach tab - Make campus-wide sustainability efforts and progress more visible
See outreach tab - Develop a procedure for integrating sustainability teaching, research and extension expertise into physical campus projects

## Integration
5-Year Tactic Template
Adopt an aggressive sustainability policy
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Create a communications and marketing plan that sends a cohesive, campus wide message regarding sustainability
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Develop a mission and vision for NC State sustainability
Tactic 1
Tactic 2
Tactic x….
Include sustainability into University strategic planning efforts
Tactic 1
Tactic 2
Tactic x…
Establish communications methods that make interactions among the CEST working groups and other diverse sustainability stakeholders easier and more consistent
Tactic 1
Tactic 2
Tactic x…
Develop and communicate the business case for campus sustainability
Tactic 1
Tactic 2
Tactic x…
Encourage the matching of student and faculty member projects to NC State’s physical campus and establishing roles for volunteers
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x…
Instill the values of total cost of ownership and total life cycle costing in to purchasing and project decision making (included in purchasing, building and integration strategies)
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x…
Investigate funding opportunities that further sustainability
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Develop a student sustainability fee to provide seed money for student sustainability projects
Tactic 1
Tactic 2
Tactic x….
Work with Advancement Office to align messaging of next university-wide campaign around energy & the environment and the needs in the classroom, buildings, infrastructure, and programming
Tactic 2
Tactic x…
Establish mechanisms to track, assess, and communicate sustainability progress
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x…
Update university guiding documents such as the master plan and design and construction guidelines to include sustainability principles (included in buildings, land use, and integration strategies)
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Create new guidelines to support sustainability activities
Tactic 1
Tactic 2
Tactic x….
Further develop the University Sustainability Office as the central location for sustainability coordination
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Position the University Sustainability Office as a unit that functions as a resource to all NC State mission areas
Tactic 1
Tactic 2
Tactic x….
Achieve better balance of sustainability project funds from institutional sources
Tactic 1
Tactic 2
Tactic x…
Serve as a coordination point for sustainability-related groups
Tactic 1
Tactic 2
Tactic x…
Continue to work with the Legislature, General Administration and other entities to further mechanisms that enable the university to meet laws
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position reponsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x…

## Outreach
5-Year Tactic Template
Begin establishing a campus culture that embraces personal responsibility and emphasizes action in creating a sustainable campus and community
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Launch campus-wide campaign utilizing community-based social marketing techniques
Tactic 1
Tactic 2
Tactic x….
Align sustainability-related outreach programs (sustainability, waste reduction and recycling, energy, alternative transportation) using a multifaceted approach
Tactic 2
Tactic x…
Make campus-wide sustainability efforts and progress more visible
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Create a coordinated local media campaign to share NC State success stories
Tactic 1
Tactic 2
Tactic x….
Integrate sustainability into NC State branding and advancement campaigns
Tactic 1
Tactic 2
Tactic x….
Standardize sustainability messaging across departments, administration and colleges
Tactic 1
Tactic 2
Tactic x….
Further develop sustainability-related event traditions such as Earth Day and Campus Sustainability Day
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Increase participation of students, faculty members, and staff in sustainability-related activities and events
Tactic 1
Tactic 2
Tactic x….
Maintain regular informal and formal networking and educational opportunities
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Develop campus wide recognition mechanisms for participating in sustainable behavior
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Develop a procedure for integrating sustainability teaching, research and extension expertise into physical campus projects
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….

## Dining
5-Year Tactic Template
Achieve a 5% increase in local and organic food purchases, above the 2010 baseline, by 2015
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Determine a baseline for local and organic food purchasing
Tactic 1
Tactic 2
Tactic x….
Track and report the percentage of total food budget spent on sustainable food
Tactic 1
Tactic 2
Tactic x…
Work with food suppliers to enhance University Dining’s tracking of local and organic foods
Tactic 1
Tactic 2
Tactic x…
Establish a local, seasonal food data base that identifies recipes that could utilize locally grown products
Tactic 1
Tactic 2
Tactic x…
Work with the franchised foodservice operations to perform a feasibility study on implementing the sustainable food service goals of University Dining
Tactic 1
Tactic 2
Tactic x…
Launch a reusable container program for take out in the dining halls
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Tactic 1
Tactic 2
Tactic x….
Launch a reusable container program for take out in the dining halls

## All
See integration tab - Adopt an aggressive sustainability policy
See integration tab - Instill the values of total cost of ownership and total life cycle costing in to purchasing and project decision making
See integration tab - Investigate funding opportunities that further sustainability
See integration tab - Continue to work with the Legislature, General Administration and other entities to further mechanisms that enable the university to meet laws
See outreach tab - Begin establishing a campus culture that embraces personal responsibility and emphasizes action in creating a sustainable campus and community
See outreach tab - Make campus-wide sustainability efforts and progress more visible
See outreach tab - Develop a procedure for integrating sustainability teaching, research and extension expertise into physical campus projects
See integration tab - Update university guiding documents such as the master plan and design and construction guidelines to include sustainability principles
See land use tab - Enhance the utilization and management of campus and building space

## Offsets
5-Year Tactic Template
Strategy
Responsible Unit(s)
Performance Indicator/Metric:
Progress Tracker (position responsible for tracking regular progress on strategies/tactics)
Tactics (Action steps for the overall strategy as well as for each sub strategy) | Responsible Position (Individual position accountable for tactic) | Milestone/Timeline (Date or indicator to establish if this tactic is on track) | Tools/Needs for Success (Policies, overcoming specific barriers, additional staff, new funds, etc)
Sub Strategy 1
Tactic 1
Tactic 2
Tactic x….
Sub Strategy 2
Tactic 1
Tactic 2
Tactic x…
Sub Strategy 3
Tactic 1
Tactic 2
Tactic x…
Sub Strategy x
Tactic 1
Tactic 2
Tactic x…